## ptc progress tracker updated 09
PTC Progress tracker updated April 2026
Housing
Name | Lead Civic | Lead organisation | Progress | Status | Updates
The Landlords Charter (private landlords) | Ken | NDC | In-progress | On track | Landlord engagement event held at the Lime Kiln Cafe on the 19 March 2026 by NDC - shared NDC team contact details for queries relating to housing complaints, housing inspections, licensing of HMOs and Park Home Sites, adaptations for disability and Energy Efficiency. Information shared about the Renters Right Act, Decent Home standards, Trading standards ‘buy with confidence’ scheme, energy and efficiency schemes. Request from attendees for pre-application planning advice and for other ways to access support as landlords. Aim - to develop a package of products and ‘bank of trades’ to support landlords as part of the Landlords charter Opportunity - NDC to think about using their Engagement HQ software (risk - is not relational approach but NDC have an intention to repeat engagement in 6 months with landlords)
Healthy Homes Ilfracombe specification (social housing) | Ken | NDC | In-progress | On track | NDDC Purchased 3 properties and made an offer on 1 other Designs are being finalised Funding is now in place but are yet to go to tender and so don't know the final costs (still doubts about fulfilling specification). NDC (Sarah-Jane) are now in a position to re-engage with the housing group to looking at a compromise re: heating Aim - Construction completed by the end of 2026. Measures will be developed to capture learning (opportunity to include lived experience in developing meaningful measures) District Council agreed to take a lead to enable this group to remain updated, have opportunities to ask for further feedback where possible, or advise on decisions being made and the reasons for this. The District Council project team are working hard to incorporate the feedback from the housing group and to date their requirements are forming part of the solutions that now need to be costed. If you still wish to be involved in the housing group, and to give permission for the Council to contact / involve you, please send a reply to nina.lake@northdevon.gov.uk
Adult Education, skills (courses) and employment (support)
Adult education courses and employment support | Steve | One Ilfracombe | In-progress | On track | One Ilfracombe have recruited a community engagement officer (Mary) The Work & skills pilot group discussed ways to improve marketing & take up of courses on offer as some have not had any referrals. North Devon College (fna Petroc) have recruited a Director of Adult Learning, who will start on the 23rd April 2026 (John Laramy, Group Principal & CEO). His line manager will be able to connect them after they start, as he is likely to be the lead contact for your group in Ilfracombe. 'We are very keen to be involved in the work in Ilfracombe and in North Devon more widely.' Learn Devon (DCC) have recruited some new tutors in the North and could begin to explore the Skills Gaps that you have identified in the work of the Poverty and Truth Commission. We have recently been delivering tailored learning short courses for 19+yrs, and potentially have the availability to plan and deliver in Ilfracombe over the next few months. DWP outreach at the Candar is still monthly as the jobcentre do not have resources to extend at present; youth hub, resource ring fenced (support services); able to provide info to childcare support to improve access; now holds funding for 19+ education (incl. Learn Devon); jobcentre local plan will review skills gap to inform delivery plan Together Drug and Alcohol Individualised Placement Support (IPS)- Together Drug and Alcohol Treatment service now have a small team of workers who identify employers who are willing to provide employment placements for people engaged in recovery and also look to buddy service users up with employers. In March 2026, they had their 1st successful placement. Rich has connected them with Charmain to discuss work in Ilfracombe that seeks to provide employment opportunities to people.
Humanise: Ilfracombe Campus development (incl. Humanise charter and 'No, but' alternative offers)
Campus model (incl. Humanise charter and 'No,but' alternative offers | Phil/James | RDUH/DMHA | In-progress | On track | Prioritised desired ‘features’ with Community Commissioners Forming working group Align with emerging opportunities - Encompass volunteer peer navigators, Integrated care pathways
Quality improvement (QI) proposal for the Ilfracombe centre | Laura | Town Council | In-progress | On track | Cllrs have allocated a small budget for changes to the Ilfracombe centre in 2026 an their is the intention to implement changes
Information window |  | One Ilfracombe | Done | n/a
Quality improvements (QI) - Wellbeing hub (Wellbeing Wednesday) | Mary / Joanie | One Ilfracombe | In-progress | On track | Social prescriber link workers are there for 2.5hrs each session to support, share information signpost during the session Services are invited to engage with the group (e.g. Energy 361)
Humanise (Principles, TAP, PHM)
Humanise principles | Richard M | Public Health Devon | In-progress | On track | Devon Public Health have: Taken principles to strategic commissioning hub (ICB) Included principles in direct award contract for 2027/28 Drug and alcohol services (Wave3) with request to evidence how they meet standards Presenting standards to SCAA and Devon Public Health team in summer 2026 Common ground CIC (working out of Co-lab Exeter) are running lived experience workshops as a space to consider the standards
Team around a person approach (TAP) | Andrea | RDUHT | In-progress | On track | TAP embedded with Health & justice (probation) project as a test and learn in Ilfracombe. information governance agreements process in place between partner legal teams to agree that data can be shared. Intention for TAP approach to be the model for complex needs Multi Disciplinary Teams work across Northern Devon. RDUH are trying to embed this approach in Royal Devon NHS Trust proposals. DPT is actively contributing to the TAP pilot, which is focussed on a defined cohort of individuals and has offered dedicated local mental health input. There has been close engagement from local service leadership, with a focus on learning what makes a practical difference for people with complex needs.
Population health management tool (Poverty inclusive) | Andrea/Ginny | RDUHT / ICB | In-progress | At risk | Andrea has created a framework incl. 20% most deprived an 'plus groups', frail, SMI, C&YP and multiple comorbidities - demonstrates need for different interventions aimed at different groups of people in need. ICB agreed to support further development (Ginny and Andrea to meet)
Cultural bids
Cultural bids | Steve | One Ilfracombe | In-progress | On track | Karen was involved as Lived experience voice.Whilst unsuccessful, the 2025 Arts Council England bid included PTC Values PTC Values were a core part of the 2026 Pride in Place bid. If shortlisted bid will be developed further and will involve people with lived experience
Staff resources (incl. Your story)
Staff resources |  | ICB / RDUHT | In-progress | On track | ICB is happy to help with the development of an ICB package. Lead - Collette Eaton-Harris - Serious Violence & Trauma Lead, Safeguarding Directorate ICB and partners creating a trauma-informed commissioning pack (work in progress) incl. importance of TI, expectation of services to deliver and measure to understand the impact of trauma. This pack will contain PTC resources (nested under 'poverty') Uses material from the PTC, ICB Trauma Stabilisation Learning Programme and TI work within RDUHT Examples of trauma informed commissioning will be referenced in the training programme (e.g. ITRS) Action - Request for ICB to share developments with PTC partners to explore integrated use (Ginny)
Your story tool |  | RDUHT | In-progress | On track | Update tbc
PTC Comms plan
Comms plan for Royal Devon NHS Trust (RDUH) | Sarah D | RDUHT | In-progress | On track | Draft comms plan created, to be signed off and shared with partners for alignment and coordinated comms

## updates
PTC Progress tracker updated 09-04-2026 | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
2799195726 | The Landlords Charter (private landlords) | Update |  | James Lander | 07/April/2026 04:22:50 PM | * Landlord engagement event held at the Lime Kiln Cafe on the 19 March - shared NDC team contact details for queries relating to housing complaints (usually tenant complaints regarding housing standards or disrepair), housing inspections, licensing of HMOs and Park Home Sites, adaptations for disability and Energy Efficiency. Information shared about the Renters Right Act, Decent Home standards, Trading standards ‘buy with confidence’ scheme, energy and efficiency schemes. Request from attendees for pre-application planning advice and for other ways to access support as landlords. * Aim to develop a package of products and bank of trades to support landlords as part of the charter * Intention to repeat engagement in 6 months with landlords * Opportunity - NDC to think about using their Engagement HQ software (risk - not relational approach) | 0 |  | 550153853
2799215983 | North Devon college | Update |  | James Lander | 08/April/2026 03:48:12 PM | (John Laramy, Group Principal & CEO) - NDC have recruited a Director of Adult Learning, who will start on the 23rd April 2026. His line manager will be able to connect them after they start, as he is likely to be the lead contact for your group in Ilfracombe. 'We are very keen to be involved in the work in Ilfracombe and in North Devon more widely.' | 0 |  | 550686946
2799195727 | Information window (The Ilfracombe centre) | Update |  | James Lander | 09/April/2026 09:43:24 AM | - Charmain is happy to take feedback to improve the window display overtime | 0 |  | 551105499
2799190013 | Quality improvements (QI) - Wellbeing hub (Wellbeing Wednesday) | Update |  | James Lander | 09/April/2026 10:14:01 AM | * Mary is no longer facilitator of Wellbeing Wednesday (volunteer led now) * Gained funding to provide refreshments and activities (warm welcome) * Social prescriber link workers are there for 2.5hrs each session to support, share information signpost during the session * 25-40 attendees each week * Services are invited to engage with the group (e.g. Energy 361) * Risk - funding * Opportunity - to measure impact with partner support and take a QI approach to improve access to services. * Potential to connect with Adult social Care re:prevention (Lynsey/Jenny/Simon) | 0 |  | 551131166
2799190158 | Quality improvement (QI) proposal for the Ilfracombe centre (incl. info window) | Update |  | James Lander | 09/April/2026 09:42:57 AM | * Cllrs have allocated a small budget for changes in 2026 an their is the intention to implement changes | 0 |  | 551105073
2799195565 | Team around a person approach (TAP) | Update |  | James Lander | 07/April/2026 04:23:26 PM | Simon Rapsey ( RDUHT) to developing process as part of Health & justice pilot (Q1/2 2026) | 0 |  | 550154017
2799195565 | Team around a person approach (TAP) | Update |  | James Lander | 08/April/2026 10:17:32 AM | * (Lynsey) RDUH are trying to embed this approach in Royal Devon NHS Trust proposals. * Embedded TAP with Health & justice (probation) project as a test and learn in Ilfracombe. information governance agreements process in place between partner legal teams to agree that data can be shared. * Intention for TAP approach to be the model for complex needs Multi Disciplinary Teams work across Northern Devon. * DPT is actively contributing to the TAP pilot, which is focussed on a defined cohort of individuals and has offered dedicated local mental health input. There has been close engagement from local service leadership, with a focus on learning what makes a practical difference for people with complex needs. Is there learning from other PTC (Phil/James) Wellbeing Exeter (Simon/Ginny/Andrea) re: information sharing? (Phil/James to ask the Poverty Truth Network) and sharing restraints around 'sensitive codes' (how we share and get the information) | 0 |  | 550424344
2799215984 | Humanise principles | Update |  | James Lander | 09/April/2026 10:35:50 AM | * Taken to strategic commissioning hub (ICB) * Devon Public Health included principles in direct award contract for 2027/28 Drug and alcohol services (Wave3) with request to evidence how they meet standards * D&A services will go bid once local government reorganisation has occured * Richard presenting standards to SCAA, Devon Public Health team in summer 2026 * working CIC Common ground CIC working out of Co-lab Exeter, running lived experience workshops as a space to consider the standards Opportunity - to hold PTC partners to the same set of standards (New objective?) and evaluate how it has made a difference * Action - Need to agree which organisations, and lead person, within PTC partner organisations will we try to embed principle in (start with Richard and Ken as there is a risk with Local Government Reorganisation) (Richard > Simon - to reach the VCSE assembly) * Survey gathering information of the support organisations would need to comply with principles | 0 |  | 551148174
2799215932 | Campus model (incl. Humanise charter) - An integrated, accessible network of support, that follows the humanise principles, enabling people to access support | Update |  | James Lander | 07/April/2026 04:23:14 PM | * Phil and James met with Community Commissioners to prioritise the desired features of the campus model (based on the design brief created by the PTC) * Forms sent to prospective Campus partners (VCSE, Civic) to gain an understanding of the level of commitment * Create a partnership between local organisations and services - Phil and James embedded within Neighbourhood Health Multi-agency meetings, to understand the impact of NHS changes | 0 |  | 550153958
2799215932 | Campus model (incl. Humanise charter) - An integrated, accessible network of support, that follows the humanise principles, enabling people to access support | Update |  | James Lander | 09/April/2026 11:09:50 AM | * Campus Model & Location of Services: There has been clear feedback through the lived experience of the PTC about the importance of location of services and at times has highlighted concerns about current service locations. DPT is actively exploring how services can and should be located and delivered locally to improve accessibility and experience. * ‘No, but’ Approach / No Wrong Door: DPT has implemented a revised internal referral approach within core mental health services. Where referrals do not meet criteria for a specific service, they should now actively be redirected to the most appropriate support in a more streamlined way. This includes clearer communication with both individuals and referrers, supporting navigation across services. * Interface with Primary Care: Referral guidance for GPs has been co-designed with local practices to improve clarity, consistency, and experience for patients. This work has been developed locally and reflects learning from lived experience, although it is not yet formalised or adopted yet as it hasn't been through the formal governance processes yet * * | 0 |  | 551177460
2799215933 | Population health management tool (Poverty inclusive) | Update |  | James Lander | 09/April/2026 09:50:40 AM | * Andrea needs ICB support (Ginny) * Andrea has created a framework incl. 20% most deprived an 'plus groups', frail, SMI, C&YP and multiple comorbidties - so that there can be different interventions aimed at different groups of people in need. | 0 |  | 551114246
2799215986 | UK town of culture 2028 bid (2026) | Update |  | James Lander | 07/April/2026 04:23:57 PM | * * Karen was involved as Lived experience voice.Whilst unsuccessful, the 2025 Arts Council England bid included PTC Values * PTC Values were a core part of the 2026 Pride in Place bid. If shortlisted bid will be developed further and will involve people with lived experience | 0 |  | 550154145
2799196776 | DWP (incl. outreach service) | Update |  | James Lander | 08/April/2026 08:40:25 AM | DWP in discussion: * create a youth Hub in North Devon - to include a dedicated day in Ilfracombe and integrate with existing services. * additional DWP support for Home educated children / NEETs (Devon wide plan), Tony will look to see what will specifically happen in Ilfracombe. DWP Action * Asked local offices to review their local plans to look at skills gaps. Tony will link the findings to any Ilfracombe specific needs. * Embarking on a multi million pound Youth Guarantee strategy later in 2026. Incl. new employer incentivised offer, Tony will work with the Ilfracombe work & Skills team to ensure Ilfracombe are represented. * Launching the Workwell programme through the Devon ICB. Tony will speak to One Northern Devon about how they may be involved, as well as some other pilots already running connected to health to see what is being targeted specifically for Ilfracombe. | 0 |  | 550340613
2799196776 | DWP (incl. outreach service) | Update |  | James Lander | 08/April/2026 01:08:56 PM | Extended DWP outreach * DWP outreach at the Candar is still monthly as the jobcentre do not have resources to extend at present. * With the youth hub, the resource would be ring fenced - will now be incorporated in the new Youth Hub proposed for north Devon. The additional benefits there would be the support services around the Youth hub. | 0 |  | 550561151
2799196776 | DWP (incl. outreach service) | Update |  | James Lander | 09/April/2026 09:33:52 AM | * DWP able to provide info to childcare support to improve access * DWP ask that people tell them if they attend * DWP now holds funding for 19+ education (incl. Learn Devon) * DWP jobcentre local plan will review skills gap to inform delivery plan Community concern - Universal credit appointment still asked to attend even when working on zero hrs contract (Tony to respond). | 0 |  | 551097947
2799196786 | Healthy Homes Ilfracombe specification (social housing) | Update |  | James Lander | 09/April/2026 10:00:53 AM | * NDDC Purchased 3 properties and made an offer on 1 other * Designs are being finalised * Funding is now in place but are yet to go to tender and so don't know the final costs (still doubts about fulfilling) * NDC (Sarah-Jane) are now in a position to re-engage with the housing group to looking at a compromise re: heating * Under construction and completed by the end of 2026 * Measure will be developed to capture learning (opportunity to include lived experience in developing meaningful measures) | 0 |  | 551121698
2799196786 | Healthy Homes Ilfracombe specification (social housing) | Update |  | James Lander | 15/April/2026 03:31:21 PM | District Council agreed to take a lead to enable this group to remain updated, have opportunities to ask for further feedback where possible, or advise on decisions being made and the reasons for this. The District Council project team are working hard to incorporate the feedback from the housing group and to date their requirements are forming part of the solutions that now need to be costed. If you still wish to be involved in the housing group, and to give permission for the Council to contact / involve you, please send a reply to nina.lake@northdevon.gov.uk | 0 |  | 554417265
2799241694 | Community engagement - Build lived experience involvement into the One Ilfracombe work and skills group | Update |  | James Lander | 09/April/2026 09:31:12 AM | * One Ilfracombe have recruited a community engagement officer (Mary) | 0 |  | 551095558
2802035898 | RDUH - 'Live Longer Better' integrated pop-up for the community rehab waiting list (Heather Wolhuter) (copy) | Update |  | James Lander | 08/April/2026 09:01:17 AM | * (Lynsey) RDUH (via Heather Wolhutter) has been exploring pop-up H&W days with One Ilfracombe discussed at the PTC - Collaborative Wellbeing Event for over 60s on Thu 30/04/2026 | 0 |  | 550362499
2825697765 | Draft comms plan for Royal Devon NHS Trust (RDUH) | Update |  | James Lander | 27/April/2026 02:03:39 PM | * RDUH comms developing comms plan | 0 |  | 565752917
2826173029 | Set up working group (book series/venue/confirm involvement) | Update |  | James Lander | 14/April/2026 03:10:40 PM | * Phil and James met with Community Commissioners to prioritise the desired features of the campus model (based on the design brief created by the PTC) * 'Commitment form' sent to prospective Campus partners (VCSE, Civic) to gain an understanding of the level of commitment | 0 |  | 553674869
2826163505 | Develop opportunities to continue to co-develop resources incl. co-developing people with lived experience | Update |  | James Lander | 09/April/2026 03:37:59 PM | * ICB and partners Trauma stabilisation training across Devon and Cornwall (ICB) - for people who don't meet criteria for MH services or MH would accept them but dealing with trauma needs to happen first * ICB and partners Trauma-informed commissioning pack - work in progress (why TI is important and give resources things ICB would expect services to deliver and measure to understand the impact of trauma) - this would be the 'space to store resource's and where PTC resources would be nested under 'poverty' * ICB have lots of material from the Trauma Stabilisation Learning Programme and from Amber’s work within RDUHT that could be pulled together into a training package. ITRS is a good example of trauma informed commissioning which we could reference in a training programme as well. ICB is happy to help with the development of an ICB package. Collette Eaton-Harris - Serious Violence & Trauma Lead, Safeguarding Directorate * Request for ICB to share with PTC partners (Ginny) * Opportunity to connect with campus (phil/James) | 0 |  | 551404123
2826168912 | Reflective practice, support and supervision for frontline staff | Update |  | James Lander | 09/April/2026 12:08:11 PM | * Paula had a positive customer experience at the North Devon Council Barnstaple hub. Opportunity to learn about best practice to inform campus/staff resources work (Acknowledge, apologised for delay, help to access online and space to use personal laptop, check-in to avoid requeuing for same issue) | 0 |  | 551232963
2826181254 | Comms & marketing plan to enable access to courses | Update |  | James Lander | 09/April/2026 09:29:14 AM | * The Work & skills pilot group discussed ways to improve marketing & take up of courses on offer as some have not had any referrals. | 0 |  | 551093957
2826184186 | Business as usual to include PTC values in all funding bids | Update |  | James Lander | 09/April/2026 09:42:09 AM | Assumption - People with lived experience will be involved Opportunity - to confirm with One Ilfracombe board to make this official) | 0 |  | 551104338
2826201346 | Learn Devon courses | Update |  | James Lander | 07/April/2026 04:23:05 PM | Learn Devon (DCC) have recruited some new tutors in the North and could begin to explore the Skills Gaps that you have identified in the work of the Poverty and Truth Commission. We have recently been delivering tailored learning short courses for 19+yrs, and potentially have the availability to plan and deliver in Ilfracombe over the next few months. | 0 |  | 550153914
2827380851 | Royal Devon NHS Trust Funding bids | Update |  | James Lander | 08/April/2026 08:58:56 AM | * (Lynsey) No funding materialised yet, but we have used learning from the PTC to inform proposals around neighbourhood teams and RDUH neighbourhood proposals (via Partnerships and Health Inequalities team). | 0 |  | 550360613
2828218976 | Royal Devon NHS Trust Board | Update |  | James Lander | 08/April/2026 01:19:46 PM | Input * Understanding of poverty video presented to Royal Devon NHS Trust board Personal impact * Many of the members later shared their own backgrounds incl. Fathers alcoholism and prison sentence; childhood with domestic violence and poverty. Organisation impact * Reminded the board of their duties under the Health & Social Care Act (not to exacerbate inequality and to engage communities in the delivery of healthcare) * Reflection on how the board cannot be sure their services are not judging people based on poverty or deprivation * The Board's reaction to this issue, their commitment to working in partnership and the link to the emerging NHSE Neighbourhood Health (prevention) should inform the entire RDUH strategy reset * Desire to share the video widely, using it for staff inductions and relevant meetings * Ensure poverty is part of the executive’s ongoing agenda (incl. Safeguarding and impact on children) * Desire to review the main board committees terms of references and/or pose a series of questions from the NHSE Health Inequalities statement for each committee to report back on i.e. does the data they receive include HI etc | 0 |  | 550573111
2830423284 | D&C Police (Joey) | Update |  | James Lander | 09/April/2026 11:02:58 AM | * Joey to identify Police work that explicitly (or aligns with) supporting people experiencing poverty (PEP) and recommendations for opportunities that the police could take to better support PEP * opportunity - Joey wants to take actions and be held accountable and be part of it | 0 |  | 551172529
2830459178 | DCC Crisis support fund | Update |  | James Lander | 09/April/2026 11:17:59 AM | DCC/NDC have an intent to co-design the crisis support fund with people with lived experience. Actions * JL requested a staff member for an in-person feedback group * Ken assigned Sarah Higgins to work with Community Commissioners to feedback on Crisis support access/expereince | 0 |  | 551183969
2830471109 | Accessible communications (Access) | Update |  | James Lander | 09/April/2026 11:26:45 AM | * Continued awareness that comms materials are not always accessible Opportunity * Connect to Campus model work/information window * Create easy read versions | 0 |  | 551190440
2830490111 | BBC spotlight | Update |  | James Lander | 09/April/2026 11:27:41 AM | People are talking about poverty (both positive an d negative) = more conversation about the PTC raised profile. > contacted by Pip and Jims about how they can support. | 0 |  | 551191122
2830493238 | Hillsdales (adult social CAre) | Update |  | James Lander | 09/April/2026 11:28:19 AM | Hilldales Care Home- Richard Merrifield (DCC Public Health) has met with Hilldales and promoted the IPTC to them and encouraged them to extend their links into the wider community. Hilldales take their residents outdoors and connect them with various activities to improve their emotional health and wellbeing. Mary confirmed Carl from Hilldales is bringing people to Wellbeing Wednesday. | 0 |  | 551191629
2830490478 | Recovery into employment (Together) | Update |  | James Lander | 09/April/2026 11:30:51 AM | Individualised Placement Support (IPS)- Together Drug and Alcohol Treatment service now have a small team of workers who identify employers who are willing to provide employment placements for people engaged in recovery and also look to buddy service users up with employers. In March 2026, they had their 1st successful placement. Rich has connected them with Charmain to discuss work in Ilfracombe that seeks to provide employment opportunities to people. | 0 |  | 551193475
2837233888 | Embedding PTC values/approach: Engage / Involve / Co-production | Update |  | James Lander | 15/April/2026 02:49:29 PM | AIM TO: Start with NHS (as employer) * ICB Ginny / Darren – policies, processes, embedding PTC learning * DPT Together (NHS) * RDUHT Engagement Sarah / Patient experience > Volunteering (Patient experience) Also ask (to fully embed PTC) * One Ilfracombe (Steve, Mary) Then local authority * Town Council * DCC co-production * Mark Doughty (advice) | 0 |  | 554373745
2838050404 | Digital Inclusion (ICB) - opportunity to update / involve commissioners | Update |  | James Lander | 13/April/2026 02:22:35 PM | ICB (NHS Devon) digital inclusion framework includes populations experiencing rural deprivation NHS Devon Digital Inclusion Place-based Delivery Plan 2026 30.12.25 (002).pdf | 0 | 216056127 | 552821964
2855132624 | Together Drug and Alcohol (DCC Public Health) | Update |  | James Lander | 20/April/2026 02:03:24 PM | Individualised Placement Support (IPS)- Together Drug and Alcohol Treatment service now have a small team of workers who identify employers who are willing to provide employment placements for people engaged in recovery and also look to buddy service users up with employers. In March 2026, they had their 1st successful placement. Rich has connected them with Charmain to discuss work in Ilfracombe that seeks to provide employment opportunities to people. | 0 |  | 562062147
2855153592 | Multi-Agency Referral meetings | Update |  | James Lander | 20/April/2026 02:05:06 PM | Multi-Agency Referral meetings (MARM)- aimed at integrating support for people whom there are safeguarding concerns/challenges services are facing with individuals- a recent case in Exeter actually included the individual whose situation was of concern in the meeting - this example must have helped overcome the issue of consent/information sharing. | 0 |  | 562063540
2855154410 | drug and alcohol rough sleeper peer support workers | Update |  | James Lander | 20/April/2026 02:07:26 PM | BtheChange a delivery partner of the STaR project in Exeter providing drug and alcohol treatment to rough sleepers have just employed 2 peer support workers. | 0 |  | 562065249
2867642763 | Connected with the Aplecollective (National Network of people with lived experience of poverty) | Update |  | James Lander | 24/April/2026 02:49:53 PM | * What have your connections with other Poverty Truth Commissions led to? We work closely with Poverty Truth Community Scotland - who are one of our members. Poverty Truth Network are very suppportive of us and have contributed to our work previously. APLE Collective members (e.g Thrive) have hosted Poverty Truth Commissions in their areas* Do you have links to the APPG (or the name of it), research and podcast? And how did you get to take part in the APPG? Yes, we work with Two APPGs - Digital Inclusion (we are a campaign partner) https://www.parallelparliament.co.uk/APPG/digital-inclusion and APPG Poverty sand Inequality (we advise them on their strategy) - https://appgpovertyinequality.org.uk/ If you would like introductions I can connect you by e mail. * I'm wondering if there is a way we can connect our work to connect with political figures (our MP and Councils are supporters of our work for example) and apply more pressure for change - Do you have any ideas? As part of APLE's work we campaign for national level lived experience voice - we campsign especially around International Day to End Poverty (17th October) to light up the UK map of lived experiemce voices. This is a UN day so often gets good attention from the press and MPs. Nationally the Poverty Truth Network can ssupport you to connect with Parliament. In terms of local councils and MPs then my suggestion would be reciprocity - how can you work with them to achieve mutual goals? E.g if there is a concultation led by the council / MP office how can you build a working relationship through that consultation and then through that working relationship ensure your message is heard. I have also found inviting councils and MPs for a photo opportunity but then catching them and spending time building working relationships over a drink or a bring and share meal is a good way to build an opportunity for them to listen. We also collaborate with larger organisations e.g Good Things Foundation / Trussell to build connections and get a way into larger spaces (e.g parliament) to have our voice heard | 0 |  | 564823451