## Sheet1
Action Log : |  | HIU Steering Group
Updated By: |  | Simon Rapsey
Date Updated: |  | 2025-12-11
*Drag down to maintain coding in column
Date action agreed | Action | Action detail | To be actioned by | Target date for Completion | RAG status | Open / Closed | Current Actions / Further Notes
#
2026-02-11 | 1 | Low Referral Numbers. Libby to review referral numbers with Graeme and explore additional ways to increase referrals into phase one, including consulting Amanda and Louise | LP | URGENT ASAP |  | Open | Referrals have increased, but still requires on-going work
2026-02-11 | 2 | Service User Engagement and Venue Preference: Libby to coordinate with Kirsty to conduct a survey or phone calls to probation service users to determine their preferred location for appointments (Ilfracombe or Barnstaple) and, if possible, ascertain reasons for their preference. | LP | 2026-02-18 |  | Closed
2026-02-11 | 7 | Data Sharing and DPIA for Stage Two: Provide contact details and storage information for each organisation’s MDT recipient to support completion of the DPIA for information sharing. (All relevant partner representatives) | All | URGENT 18/02/2026 |  | Open | RDUH DPIA complete now. Partners to complete. ISA to sign.
2026-02-11 | 3 | Probation Officer Involvement in Stage Two: Clarify and confirm who from probation will be involved in the stage two 'what matters' conversation alongside Glenda, and communicate this to the group. | LP | 2026-02-18 |  | Closed
2026-02-11 | 4 | Kafka Brigade Participant Identification: Contact the first gentleman who received a health check to discuss participation in the Kafka Brigade, and follow up with Graeme regarding another potential participant previously interviewed. (Glenda, Andrea) | LP | 2026-02-25 |  | Closed | One recruit booked for interview.
2026-02-11 | 5 | Kafka Brigade Senior Representation: Send details of the appropriate senior contact for the Devon and Cornwall district leader to the group for Kafka Brigade involvement. | Tony | 2026-02-18 |  | Open
2026-02-11 | 6 | Kafka Brigade Senior Representation: Identify and confirm the highest appropriate senior representative from probation (e.g., Becky Hart) to attend the Kafka Brigade collective performance review. | Libby/Dave | 2026-02-18 |  | Closed
2026-02-11 | 8 | Probation Data Recording Accuracy: Speak with Sarah Jones to ensure that probation appointments in Ilfracombe are being accurately recorded in the system and address any discrepancies. (Dave) | Dave | 2026-02-25 |  | Open
2026-04-01 | 9 | Probation Operational Engagement: Invite Sarah Jones and Victoria Barnes to future meetings to ensure operational probation staff are engaged and able to support project delivery. (Andrea) | Andrea | 2026-04-29 |  | Open
2026-04-01 | 10 | DPIA and Data Sharing Progression: Nudge Martin (Devon County Council IG lead) regarding the DPIA and data sharing agreement for the MDT, and confirm status with Amy if necessary. (Nicholas) | Nicholas | 2026-04-29 |  | Open
2026-04-01 | 11 | Referral Process for Post-Probation Support: Develop a plan with Graeme, Glenda, and Jeanette to ensure continuity of care and support for individuals after probation ends, including potential warm handovers to primary care or wellbeing teams. (Glenda, Jeanette, Graeme) | Glenda, Jeanette, Graeme | 2026-04-29 |  | Open
.
.