## Sheet1
Action Log : |  | HIU Steering Group
Updated By: |  | Simon Rapsey
Date Updated: |  | 2025-12-11
*Drag down to maintain coding in column
Date action agreed | Action | Action detail | To be actioned by | Target date for Completion | RAG status | Open / Closed | Current Actions / Further Notes
#
2026-02-11 | 1 | Low Referral Numbers. Libby to review referral numbers with Graeme and explore additional ways to increase referrals into phase one, including consulting Amanda and Louise | LP | URGENT ASAP |  | Open
2026-02-11 | 2 | Service User Engagement and Venue Preference: Libby to coordinate with Kirsty to conduct a survey or phone calls to probation service users to determine their preferred location for appointments (Ilfracombe or Barnstaple) and, if possible, ascertain reasons for their preference. | LP | 2026-02-18 |  | Open
2026-02-11 | 7 | Data Sharing and DPIA for Stage Two: Provide contact details and storage information for each organisation’s MDT recipient to support completion of the DPIA for information sharing. (All relevant partner representatives) | All | URGENT 18/02/2026 |  | Open
2026-02-11 | 3 | Probation Officer Involvement in Stage Two: Clarify and confirm who from probation will be involved in the stage two 'what matters' conversation alongside Glenda, and communicate this to the group. | LP | 2026-02-18 |  | Open
2026-02-11 | 4 | Kafka Brigade Participant Identification: Contact the first gentleman who received a health check to discuss participation in the Kafka Brigade, and follow up with Graeme regarding another potential participant previously interviewed. (Glenda, Andrea) | LP | 2026-02-25 |  | Open
2026-02-11 | 5 | Kafka Brigade Senior Representation: Send details of the appropriate senior contact for the Devon and Cornwall district leader to the group for Kafka Brigade involvement. | Tony | 2026-02-18 |  | Open
2026-02-11 | 6 | Kafka Brigade Senior Representation: Identify and confirm the highest appropriate senior representative from probation (e.g., Becky Hart) to attend the Kafka Brigade collective performance review. | Libby/Dave | 2026-02-18 |  | Open
2026-02-11 | 8 | Probation Data Recording Accuracy: Speak with Sarah Jones to ensure that probation appointments in Ilfracombe are being accurately recorded in the system and address any discrepancies. (Dave) | Dave | 2026-02-25 |  | Open